## List1
# | Status | Severity | Place | Issue description | Possible solution | Affected OS
2.1.8
GUI:
1 | Done | highest | all | Make sure subprocess is killed when GUI dies | Loop is checking if GUI lives if not kills subprocess | all
2 | Done | highest | all | Subprocess output to a TextBox | Process events after every single line, see #6 | all
21 |  | highest | Reencode | If video already exists there is now way to press y/n | Auto numbering? | all
20 |  | high | Reencode | Ree does not support whole folder re-encode | depends on subs playlist downlosad for now | all
18 |  | high | Subs | Sub download does not support playlist download | if supported in yt-dl than with more loops possible | all
3 | Done | high | Audio | Audio download | Somewhat works | all
4 | Done | high | all | You can start subpocess more than once download button | Shown in the status, will throw a message box | all
19 | Done | high | all | Button that opens your downloads forder | Useful as fuck | all
22 | Posponed | high | AutoUpd | Autoupdate on start updates first but does not start UI |  | all
5 | Done | medium | Settings | Remember to save download path with double separator at the end | Check path saving more carefully | Windows
6 | Done | medium | all | UI runs really slowly while subprocess writing to TextBox | I don't think I can fix that so I show satus | all
7 | Done | medium | About | Link on a TextBox was opening in TextBox instead of external app | Allowing openExternalLinks | all
8 | Done | medium | all | Get over initial hurdles of QtDesigner, Qt & window resizing | Reading testing | all
9 | Done | medium | all | ffapps in directory gui support subprocess | List magics | all
14 | Done | medium | all | all the downloading lines are taken as a single line | posible fix switch back to the character by character rendering | all
15 | Canceled | medium | all | Learn how to move cursor to begining of current line QTextBrowser | will make the download look nicer | all
10 | Done | low | all | Change UI colors | More QtDesigner learning | all
11 | Done | low | all | Download in a specific tab could be shown by * or color of tab | Starting audio download would change tab name | all
12 |  | low | all | Colors changeble in config | use settings.json | all
17 |  | low | Subs,Reencode | ffmpeg now hides banner, maybe I could add some debug | to see waht ffmpeg version I'm using | all
CLI:
13 |  | medium | all | Bring Loadpath code up to date with changes in gui | better order and error handling | all
16 |  | medium | Subs | Sub download (long untouched) does not suppot ffmpeg from dir | I wrote sub download and than let it be a black box | all
2.1.9
GUI:
1 |  | highest | all | GUI redesign | Even tho 2.1.8 is not done it already needs to be planned | all
2 |  | high | Audio,Subs | Audio & Sub tab does not have to exist | It can all be download tab with radio buttons | all
3 |  | medium | all | Official Hubz design Edition | Please and thank you mister hubz the designer | all